## Sprint 1
DATE | User Story | TO DO | In Progress | Impediment | To Verify | Done
26-08-22 | 1. Create Student table, Institute table, Schelarship application table. [Ritam Chakladar] | 1.1 Discuss about the database design 1.2 Create student table 1.3 Create Institute table 1.4 Create Scholarship Application table 1.5 Generate Angular and .NET Core Web Api project |  |  |  | 1.1 Discussed about the database design 1.2 Created student table 1.3 Created Institute table 1.4 Created Scholarship Application table 1.5 Generated the Angular and .NET Core Web Api project
| 2. Create Ministry table, Officer table,Scholarship Application table. [Ashok J] | 2.1 Discuss about the database design 2.2 Create ministry table 2.3 Create officer table 2.4 Create Scholarship Application table 2.5 Add some contraints on the table of the database |  |  |  | 2.1 Discussed about the database design 2.2 Created ministry table 2.3 Created officer table 2.4 Create dScholarship Application table 2.5 Added some contraints on the table of the database
| 3. Design the HTML Pageof the portal and navbar | 3.1 Discuss about the database design 3.2 Create the Contact page 3.3 Create the Navbar 2.4 Add routing to the navbar |  |  |  | 3.1 Discussed about the database design 3.2 Created Contact us Page 3.3 Created Navbar 3.4 Added routing to navbar
| 4. Design the Home and About Us HTML pages. [Prashant Chauhan] | 4.1 Discuss about the database design 4.2 Create the Home page 4.3 Create the About Us page 4.4 Add routing to the HTML pages |  |  |  | 4.1 Discussed about the database design 4.2 Created Home Page 4.3 Created About Us Page 4.4 Added routing to the HTML pages
27-08-22 | 1. Create Student, Create Institute, Get Students, Get Institutes, Create Scholarship application form, View Schemes [Ritam Chakladar] | 1.1 Develop constrollers for creating students 1.2 Develop constrollers for creating institutes 1.3 Develop constrollers for fetching students 1.4 Develop constrollers for fetching institutes 1.5 Develop constrollers for creating applications 1.6 Add error and exception handling to student controller 1.7 Test student controller using postman 1.8 Develop controllers for checking the status of the applications 1.9 Develop constrollers to get all the available schemes, scheme by id and delete scheme |  |  |  | 1.1 Developed constrollers for creating students 1.2 Developed constrollers for creating institutes 1.3 Developed constrollers for fetching students 1.4 Developed constrollers for fetching institutes 1.5 Developed constrollers for creating applications 1.6 Added error and exception handling to student controller 1.7 Tested student controller using postman 1.8 Developed controllers for checking the status of the applications 1.9 Developedconstrollers to get all the available schemes, scheme by id and delete scheme
| 2. Create Controller for institute and add all methods . [Ashok J] | 2.1 Create Controller for Institute. 2.2 Develop controller to get all students from the institute 2.3 Develop controller for registeration fo the institute. 2.4 Develop controller to get all students scholarship application forms 2.5 Develop controller for approving the student scholarship form. 2.6 Develop controller to check the status of the institute registeration approval 2.7 Develop controller for rejecting the student scholarship form. 2.8 Develop controller to get all approved student scholarship form 2.9 Develop controller to get all institutes. |  |  |  | 2.1 Created Controller for Institute. 2.2 Developed controller to get all students from the institute 2.3 Developed controller for registeration fo the institute. 2.4 Developed controller to get all students scholarship application forms 2.5 Developed controller for approving the student scholarship form. 2.6 Developed controller to check the status of the institute registeration approval 2.7 Developed controller for rejecting the student scholarship form. 2.8 Developed controller to get all approved student scholarship form 2.9 Developed controller to get all institutes.
| 2. Create Controller for Officer and add all methods . [Jovita DLima] | 3.1 Create Controller for Officer. 3.2Develop method for Nodal officer Login 3.3 Develop method to get list of institutes pending for approval by officer 3.4Develop method to get details of institutes pending for approval by officer. |  |  |  | 3.1 Created Controller for Officer. 3.2 Developed method for Nodal Officer Login 3.3 method to get list of institutes oending approval by officer 3.4 Developed method to get details of institutes pending for approvasl by officer.
| 4. Create Controller for Ministry and add all methods. [Prashant Chauhan] | 4.1 Create Controller for Ministry. 4.2 Develop method for Ministry Login 4.3 Develop method to get list of institutes pending for approval by ministry 4.4 Develop method to get details of scholarship application forms pending for approval by ministry. |  |  |  | 4.1 Created Controller for Ministry. 4.2 Developed method for Ministry Login 4.3 Developed method to get list of institutes pending for approval by ministry 4.4 Developed method to get details of scholarship application forms pending for approval by ministry.
29-08-22 | 1. Student Register and Login, Institute Register and Login, Ministry login, Officer login. [Ritam Chakladar] | 1.1 Develop constrollers for student register and login 1.2 Develop constrollers for institute register and login 1.3 Develop constrollers for officer login 1.4 Develop constrollers for ministry login 1.5 Develop method to create hash of user password to store in database 1.6 Develop method to generate jwt tokens 1.7 Test authentication using postman 1.8 Develop Scholarship application form UI (angular) 1.9 Develop Login pages UI for student, institute, ministry and officer (angular) 1.10 Implement form validation for student, institute, ministry and officer login components (angular) | Implementation of form validation for student, institute, ministry and officer login components (angular) |  |  | 1.1 Developed constrollers for student register and login 1.2 Developed constrollers for institute register and login 1.3 Developed constrollers for officer login 1.4 Developed constrollers for ministry login 1.5 Developed method to create hash of user password to store in database 1.6 Developed method to generate jwt tokens 1.7 Tested authentication using postman 1.8 Developed Scholarship application form UI (angular) 1.9 Developed Login pages UI for student, institute, ministry and office
| 2. Add some methods in Ministry and Officer Controller and Creating Ministry Component [Ashok J] | 2.1 Add reject institute appliaction in the officer controller and ministry controller 2.2 Add reject scholarship application in the ministry controller and officer controller 2.3 Create Ministry Component in the angular. 2.4 Develop the dashboard component in the ministry component. 2.5 Develop view scholarship application in the ministry component. 2.6 Develop view institute application in the ministry component 2.7 Implement the upload document function in the controllers |  |  |  | 2.1 Added reject institute appliaction in the officer controller and ministry controller 2.2 Added reject scholarship application in the ministry controller and officer controller 2.3 Created Ministry Component in the angular. 2.4 Developed the dashboard component in the ministry component. 2.5 Developed view scholarship application in the ministry component. 2.6 Developed view institute application in the ministry component
| 2. Add some methods in Officer Controller and Creating Officer Component [Jovita DLima] | 3.1 Develop method to get unapproved student applications. 3.2. Develop method to get scholarship applications by ID 3.3 Develop method to get scholarship applications by ID 3.4 Develop method to verify Institute 3.4 Develop method toreject institute 3.5 Develop method to verrify scholarship application 3.6 Develop method to reject scholarship application |  |  |  | 3.1 Developed method to get unapproved student applications. 3.2. Developed method to get scholarship applications by ID 3.3 Developed method to get scholarship applications by ID 3.4 Developed method to verify Institute 3.4 Developed method toreject institute
| 4. Add some methods in Institute Controller and Creating Institute Component, Create Institute Registration Form, Scholarship Application Form Validation. [Prashant Chauhan] | 4.1 Develop method to verify all the Student Applications 4.2 Develop method to reject Student Application 4.3 Create Institute Registraion Form 4.4 Do the front end part of Institute Component 4.5 Implement form validation for Scholorship Apllication form 4.6 Test the form validation |  |  |  | 4.1 Developed method to verify all the Student Applications 4.2 Developed method to reject Student Application 4.3 Created Institute Registraion Form 4.4 Created the front end part of Institute Component 4.5 Implemented form validation for Scholorship Apllication form 4.6 Tested the form validation

## Sprint 2
DATE | User Story | TO DO | In Progress | Impediment | To Verify | Done
30-08-22 | 1. Student Register and Login, Institute Register and Login, Ministry login, Officer login, Institute Approve Application (Frontend and Backend) [Ritam Chakladar] | 1.1 Integrate frontend and backend for student register and login 1.2 Integrate frontend and backend for institute register and login 1.3 Integrate frontend and backend for officer login 1.4 Integrate frontend and backend for ministry login 1.5 Fix bugs present in database seeding while creating ministry and officer data in database 1.6 Implement form validation for student, institute, ministry and officer components (angular) 1.7 Develop controllers for approve and reject application in institute 1.8 Test controllers for approve and reject application in postman 1.9 Integrate frontend and backend for approve and reject application by institute 1.10 Fix bugs present in the angular routes |  |  |  | 1.1 Integrated frontend and backend for student register and login 1.2 Integrated frontend and backend for institute register and login 1.3 Integrated frontend and backend for officer login 1.4 Integrated frontend and backend for ministry login 1.5 Fixed bugs present in database seeding while creating ministry and officer data in database 1.6 Implemented form validation for student, institute, ministry and officer components (angular) 1.7 Developed controllers for approve and reject application in institute 1.8 Tested controllers for approve and reject application in postman 1.9 Integrateed frontend and backend for approve and reject application by institute 1.10 Fixed bugs present in the angular routes
| 2. Integration of Ministry Component and Officer Component. [Ashok J] | 2.1 Test the controllers of officer in the postman 2.2 Test the controllers of ministry in the postman 2.3 Integrate Front end and back end of the ministry approve and reject institute application. 2.4 Integrate Front end and back end of the officer approve and reject institute application. 2.5 Add Scheme create, delete, delete functions in the ministry controller 2.6 Integrate Front end and backend of the ministry scheme create, delete, edit. |  |  |  | 2.1 Tested the controllers of officer in the postman 2.2 Tested the controllers of ministry in the postman 2.3 Integrated Front end and back end of the ministry approve and reject institute application. 2.4 Integrated Front end and back end of the officer approve and reject institute application. 2.5 Added Scheme create, delete, delete functions in the ministry controller 2.6 Integrated Front end and backend of the ministry scheme create, delete, edit.
| Form validation and Officer component [Jovita DLima] | 3.1 Implement form validation for Institute Registration 3.2 Test the form validation 3.3 Implement Officer component 3.4 Implement routing in angular 3.5 Upload form data on server for testing purpose | 3.1 Develop method to verify institute 3.2 Implement method to reject institute |  |  | 3.1 Implemented form validation for Institute Registration 3.2 Tested the form validation 3.3 Implemented Officer component 3.4 Implement edrouting in angular 3.5 Developed method to verify scholarwship application 3.6 Developed method to reject scholarship application
| 4. Scholarship Application Form Integration with Backend and Ministry component. [Prashant Chauhan] | 4.1 Integration of Scholorship Apllication form with Backend 4.2 Test the form Integration 4.3 Implement Ministry component 4.4 Implement routing in angular 4.5 Upload the form data on the server (for checking purpose only) |  |  |  | 4.1 Done Integration of Scholorship Apllication form with Backend 4.2 Tested the form Integration 4.3 Implemented Institute component 4.4 Implement routing in angular 4.5 Developed method to verify Institute Application 4.6 Developed method to reject Institute application 4.7 Developed method to verify Scholarship Application 4.8 Developed method to reject Scholarship application
2022-01-09 | 1. Error handling frontend, Bug fixes, New constrainsts in controllers, File upload angular. [Ritam Chakladar] | 1.1 Add error handling in angular 1.2 Fix existing bugs present in the student and institute constrollers 1.3 Add more check conditions while registering students and institutes 1.4 Test student and institute controllers in postman 1.5 Add toast notifications in angular 1.6 Fix UI styles in frontend 1.7 Implement File upload feature in Angular 1.8 Add FAQs in student dashboard 1.9 Add status message in applications for student and institute 1.10 Fix the database relation between student and application table |  | Facing problems while uploading files from frontend to backend. |  | 1.1 Added error handling in angular 1.2 Fixed existing bugs present in the student and institute constrollers 1.3 Added more check conditions while registering students and institutes 1.4 Tested student and institute controllers in postman 1.5 Added toast notifications in angular 1.6 Fixed UI styles in frontend 1.7 Implemented File upload feature in Angular 1.8 Added FAQs in student dashboard 1.9 Added status message in applications for student and institute 1.10 Fixed the database relation between student and application table
| 2. Fix Bugs in the Controllers and in the Components [Ashok J] | 2.1 Test the working of Ministry after the integration 2.2 Test the working of Office after the inegration 2.3 Fix the bugs in the Office Controller 2.4 Fix the bugs in the Ministry Controller 2.5 Fix the bugs in the Officer Component 2.6 Fix the bugs in the Ministry Component 2.7 Add the Institute Application Detail View in the Ministry Component 2.8 Add the Institute Application Detail View in the Ministry Component 2.9 Add the Institute Application Detail View in the Officer Component 2.10 Add the Scholarship Application Detail View in the Ministry Component 2.11 Add the Scholarship Application Detail View in the Officer Component | 1.Back end of registration almost done where i am able to extract and save data in data base. Now inserting all the required fields. |  |  | 2.1 Tested the working of Ministry after the integration 2.2 Tested the working of Office after the inegration 2.3 Fixed the bugs in the Office Controller 2.4 Fixed the bugs in the Ministry Controller 2.5 Fixed the bugs in the Officer Component 2.6 Fixed the bugs in the Ministry Component 2.7 Added the Institute Application Detail View in the Ministry Component 2.8 Added the Institute Application Detail View in the Ministry Component 2.9 Added the Institute Application Detail View in the Officer Component 2.10 Added the Scholarship Application Detail View in the Ministry Component 2.11 Added the Scholarship Application Detail View in the Officer Component
| Improve UI design and fix bugs [Jovita DLima] | 3.1 Make changes and improve the UI pages of student and institute 3.2 Adding routing to buttons and navbar 3.3Addition of few more things in the frontend |  |  |  | 3.1 Made changes and improve the UI pages of student and institute 3.2 Added routing to buttons and navbar 3.3Addition of few more things in the frontend
| 4. Improve UI design and fix bugs. [Prashant Chauhan] | 4.1 Make changes and improve the UI pages of Officer and Ministry 4.2 Adding routing to buttons and navbar 4.3 Addition of few more things in the frontend | Addition of few more validations Addition of Few more things in FrontEnd, Dashboard, Routing, Redirection |  |  | 4.1 Made changes and improve the UI pages of Officer and Ministry 4.2 Added routing to buttons and navbar 4.3 Addition of few more things in the frontend